## Sheet1
Task Name | Duration | Start | Predecessors | Finish | % Complete | Status | Comments
Sprint #1: Requirement Mapping | 14d | 2021-09-06 |  | 2021-09-20 | 100% | Complete
Product Backlog
User Story Creation and task breakdown
Sprint #2: Feature Design | 10d | 2021-10-08 |  | 2021-10-18 | 100% | Complete
Understand the data to be analyzed
Design the reports, dashboard and chart features
Sprint #3: Development | 7d | 2021-10-18 |  | 2021-10-25 | 100% | Complete
Identified data flow
Confirmed assumptions
Created initial docker with api and postgresql
Sprint #4: Development | 7d | 2021-10-25 |  | 2021-11-01 | 100% | Complete
Explore handling core data type
Added methods to find type of the IG passed
Methods to handle flags sent by users
Sprint #5: Development | 7d | 2021-11-01 |  | 2021-11-08 | 100% | Complete
Added Synthea docker to application
Add all the profiles for us-core IG
Mapped default values for primitive datatypes
Added method to retrieve all attributes from IG
Sprint #6 : Development | 7d | 2021-11-08 |  | 2021-11-15 | 100% | Complete
Added method to generate values for Primitive datatypes
Integrated with Swagger UI
Created API and skeleton methods for each controller
Added method to fetch all missing attributes from Synthea
Sprint #7 : Development and Testing | 7d | 2021-11-15 |  | 2021-11-22 | 100% | Complete
Added profiles for ips and qi-core
Feature to generate data for complex datatype
Tested the app on different implementation guides
Functionality to dynamically handle implementation guides
Sprint #8 : Development and Testing | 7d | 2021-11-22 |  | 2021-11-29 | 100% | Complete
Identified issue with logic while getting data from Synthea and fixed it
Modified data structure to use multimap to store data read from Synthea
Added class to generate examples by using all previously created methods
Sprint #9 : Development and Testing | 7d | 2021-11-29 |  | 2021-12-06 | 100% | Complete
Added flags support to example generator method
Fixed logic in the method for missingAttributesForSynthea
Added API to render example data
Refactored code to remove multiple reads of profiles
Updated API to support flags from users
Sprint #10 : Testing, Sprint Review and Demo | 7d | 2021-12-06 |  | 2021-12-13 | 100% | Complete
Final testing
Documentations
Demo